## Slide 1: FastTrack for Dynamics 365
<NAME>
<Job Title>
Cutover Strategy Workshop
Created On: dd/MM/yyyy

## Slide 2: Cutover Strategy Workshop Agenda
Agenda
The Cutover Strategy workshop is designed to ensure that the cutover strategy provides a good approach and plan to deliver a well-defined, well-tested, reliable, and safe transition from current systems to the new production systems.
Cutover Vision & Strategy
Cutover Project Plan
Go-Live Cutover Plan
Post Go-Live Plan
Format: 120-minute Microsoft Teams call
Attendees: Cutover Lead, Solution Architect, Data Migration Lead and Project Manager roles are mandatory.
Other roles that may attend are Technical Leads and Functional Leads
Q/A & Next Steps

## Slide 3: Cutover Vision & Strategy

## Slide 4: Business Aims & Goals
Describe the aims or goals of the cutover from a business perspective.
Enter Details Here
Customer slide (please update)
Who is the designated cutover leader and what is the scope of their responsibilities?
Add Info Here
Describe the responsibilities and ownership of the key cutover activities (like data cleansing, data migration, communication, etc)?
Add Info Here

## Slide 5: Cutover Scope & Strategy
Describe the full scope that is intended to be covered by the cutover
Enter Details Here
Customer slide (please update)
Describe the high-level strategy for the cutover
Enter Details Here

## Slide 6: Cutover Calendar
Describe the calendar of key business activities that will take place leading to, and during the cutover.
Enter Details Here
Provide an example
Customer slide (please update)
Notes: Cutover Planning
Cutover planning must be integrated into project macro plan and sprint plans
Cutover must include all activities related to Go Live – not just data migration
Set cutover discipline form the start and plan for multiple (5 to 7) trial cutovers – at least 2 successful ones prior the real Go-Live
Each cutover should have explicit entry and exit criteria (including performance criteria)
Gap/issues/bugs from cutover need to be registered as bug/actions, triaged and managed as any other bug/actions
Need input and ownership from partner as cutover directly touches solution architecture and functional use.

## Slide 7: Cutover Project Plan

## Slide 8: High-level Cutover Project Plan
Please describe and include a copy of your cutover project plan.
Enter Details Here
Customer slide (please update)
Notes: Overall approach
Start with the cutover vision, principles and a designated cutover leader
Create a business-focused cutover calendar
Create a detailed strategy
  Business calendar activities (not only data migration)
  Roles and responsibilities
  Dependencies
  High-level cutover project plan with mock cutovers
  Cutover fallback plan and rules
  Reconciliations – what’s needed and how done, source data cleaning toolkit
  Environment management plan
  Assess impact on ecosystem and identify other owners
Create the detailed cutover plan
Involve the business early, often and ensure ownership

## Slide 9: Data Cutover
What are the Data Migration processes (and milestones) that are managed by, or integrated with, the cutover management process?
How many data migration runs (as part of the mock cutover) have been completed and with what level of success ?
Add Info Here – Reference the Data Migration Strategy/Workshop as needed.
Add Info Here – Reference the Data Migration Strategy/Workshop as needed.
What is the detailed Data Cutover strategy?
Customer slide (please update)
Add Info Here
Notes: Data Loading
Entity sequence definition, including incremental load for high-volume entities
Best practices for loading data into D365
  Automate only if rules are well defined and compete
  Strive to make load repeatable: automate and simplify process
  Define entities that will be complete and perform well
  Set performance goals, simplify the process
  Small transaction scope, multi-thread where appropriate
  Replicate production environment for perf testing
Early validation and repeat

## Slide 10: System Cutover
What are the system cutover processes (and milestones) that are managed by, or integrated with, the cutover management process?
Add Info Here – Reference the Data Migration Strategy/Workshop as needed.
Add Info Here – Reference the Data Migration Strategy/Workshop as needed.
What is the detailed system cutover strategy including the agreed legacy system shutdown process with the date and times?
Customer slide (please update)
Notes: Data Loading
Entity sequence definition, including incremental load for high-volume entities
Best practices for loading data into D365
  Automate only if rules are well defined and compete
  Strive to make load repeatable: automate and simplify process
  Define entities that will be complete and perform well
  Set performance goals, simplify the process
  Small transaction scope, multi-thread where appropriate
  Replicate production environment for perf testing
Early validation and repeat

## Slide 11: Testing & Mock-Cutovers
What are the entry/exit criteria for mock cutovers?
Add Info Here
How, when and where are the mock cutovers conducted and how are you validating the cutover process and the resulting systems?
Add Info Here
Customer slide (please update)

## Slide 12: Timing & Performance
How long is the final end-to-end cutover expected to take?
What day and time will the final cutover start and when is the new system expected to be live?
Add Info Here
Add Info Here
What are the high-risk areas for performance during the cutover and how are they being addressed?
Add Info Here
Customer slide (please update)

## Slide 13: Change Management
Describe how change management has been implemented and communicated with the business users throughout the project as it relates to the implications of the cutover strategy.
Add Info Here
Customer slide (please update)

## Slide 14: Environment Plan – Human Resources
Which environment is currently used as the GOLD environment?
What is the strategy to move from GOLD to PROD?
Add Info Here
Add Info Here
Describe the environment strategy for the mock go-lives.
Add Info Here
Customer slide (please update)

## Slide 15: Environment Plan – F&O
Which environment is currently used as the GOLD environment?
What is the strategy to move from GOLD to PROD?
Add Info Here
Add Info Here
Describe the environment strategy for the mock go-lives.
Add Info Here
Customer slide (please update)

## Slide 16: Environment Plan – CE
Which environment(s) will be used to support the mock go-live activities?
Add Info Here
Add Info Here
Describe the environment strategy for the mock go-live.
Customer slide (please update)

## Slide 17: Go-Live Cutover Plan

## Slide 18: Go-Live Cutover Organization
Describe the organizational structure that will manage, perform, validate and approve the final Go-Live cutover and the related communication plan
Enter Details Here
Provide notes for additional context on what is expected
Customer slide (please update)

## Slide 19: Final Go-Live Detailed Cutover Plan
Describe the key elements of the Go-Live cutover plan and attach a copy of the current draft here
Enter Details Here
Add to Notes, text on a sample cutover plan they can download if needed
**Add Sample cutover columns.xls from background folder
Customer slide (please update)

## Slide 20: Go/No-Go & Rollback Plans
Describe the Go/No-Go decision points and when they will be made
Enter Details Here
Customer slide (please update)
Describe the criteria for invoking rollback and/or contingency and the plans for executing them
Enter Details Here

## Slide 21: Remote Go-Live – Key Considerations
Communication – Organization
Communication – People
Communication – Strategy and technology
Communication, Communication, Communication
Notes: Main Additional Risks to Manage:
Easy to underestimate the impact of the remote Go-Live!
Behavior & level of engagement changes when working remotely
Unclear communication channels
Unclear communication patterns
Unclear rules of engagement
Hermits, ghosts and “squeaky wheels”
Decentralized process ownership  lack of control
Over-centralized ownership  lack of reactivity and effectiveness
Technical issues
Human factors

## Slide 22: Communication Plan Strategy Example
Coordinator
Stream/area leaders
Task owners
Issues manager
The coordinator runs the process
The area leaders verify the task execution and unblock issues (decision makers)
Task owners execute the tasks
Issue manager coordinates problems resolution in parallel with the “normal” execution

## Slide 23: Remote Go-Live Considerations
How is the cutover management strategy being designed to work effectively and efficiently for a Remote Go-Live?
Add Info Here
Customer slide (please update)
Notes: For remote Go Live tasks need to be:
    more detailed and more precise
    better definition of the responsibility
    push for a buddy system where possible, as hard for individuals to take the burden otherwise
Tasks for business users need to be especially carefully prepared with the principles above in mind
Increase the buffer between key stages to give you more reliability for those who only have a few (key) tasks to perform.
Have a “cutover Go Live board” or shared Excel which everyone can view, but only editable by the cutover organizer (and substitute).
Set more frequent and specific team review gates
Ownership and organization
There must be a strong coordinator to run the whole process.
Responsibilities defined for everyone
    Leaders for each area of the cutover to ensure “expert” coordination and decision making
    Responsibility for each task assigned to a specific person
    Need to explicitly secure availability, especially for business users and key partner resources
Appoint an area-level issue manager/leader
    Area-level issue board with recurring update
    Map all the issues to some cutover task to ensure traceability and dependences are clear
    Avoid area-level issues from blocking the whole cutover or dragging everyone into the discussion
Double-check agreements by all stakeholders for business and system blackout and business involvement
Technical preparation
Provide training on remote tools (Teams, RDP, etc) and ensure they are working prior to the cutover, especially for non-technical people
Validation of remote access communications (Teams – Screen share etc..) with defined backups (e.g. teleconference phone, SMS etc)
Validation for data access (VPNs, Firewalls, credentials etc)
Consider if someone with admin access needs to be on-site for any legacy systems access or emergencies
Internet connection and bandwidth for everyone
Security/Regulations: can data leave the premises where/if needed?
Human factor
Buddy system where possible
Efficiency improvement – avoid unwritten or untold microtasks
High task granularity helps to control and allows handovers

## Slide 24: Post Go-Live

## Slide 25: Post Go-Live Activities
Describe the process and planning for transition from project to support (esp with respect to the cutover and immediate hyper care period)
Enter Details Here
Customer slide (please update)
Describe any post Go-Live cutover activities and how they will be managed
Enter Details Here
Describe the exit criteria and strategy for the cutover process and cutover organization
Enter Details Here

## Slide 26: Q/A & Next Steps

## Slide 27: Q&A
Brief Q&A to discuss any additional topic areas.
List questions and follow up actions
Customer slide (please update)

## Slide 28: Next Steps
Discuss next steps and action items.
List next steps and action items
Customer slide (please update)
Notes: Post Go-Live Considerations
Performance issues.
  Backlog of business – impact on batch process - plan starts to throttle.
  Test the day in a life scenario with full- or almost full-scale
User adoption and Feedback channels
  People that finds workaround on things that they don't really understand - implications
  Adoption / change management is the key as harder to communicate as colleagues.
  Prepare people to rase issues and give them tools to collaborate – eg Teams channels
  First weeks the rate of business might slow – ensure stakeholder support
  Tighter connected departments, functional areas and processes – harder with a new system
  Champions in each department can help – enthusiasm is contagious as rejection
  In remote context, can be useful planning for user sessions, surgery hours and let the users express their issues and doubts.
Date migration can show issues after two/three weeks
  Full business transaction lifecycle process testing on migrated data can help

## Slide 29: Copyright Microsoft
© 2020 Microsoft Corporation. All rights reserved. Microsoft, Microsoft Dynamics, Office 365, Windows, and other product names are or may be registered trademarks and/or trademarks in the U.S. and/or other countries. The information herein is for informational purposes only and represents the current view of Microsoft Corporation as of the date of this presentation. Because Microsoft must respond to changing market conditions, it should not be interpreted to be a commitment on the part of Microsoft, and Microsoft cannot guarantee the accuracy of any information provided after the date of this presentation. MICROSOFT MAKES NO WARRANTIES, EXPRESS, IMPLIED OR STATUTORY, AS TO THE INFORMATION IN THIS PRESENTATION