## Slide 1: Dynamics 365 Data Migration Strategy Workshop
<NAME>
Solution Architect
24 August 2021

## Slide 2: Data Migration Strategy Workshop Agenda
Strategy workshop is designed to help ensure that the project team’s approach to data migration is following best practices, including timing, to avoid data migration performance issues, understanding of business goals, and awareness on realistic throughput
Agenda
Data Management Strategy
Planning and Strategy
Data Volume
Tooling
Data Validation
Format: 2 hours Microsoft Teams call
Attendees: Solution architects, functional and technical leads at minimum; project managers, functional leads and other key stakeholders from the customer and partner teams.
Testing
Q&A
Performance
The Data Migration Strategy Workshop is designed to help ensuring that the approach for data migration is heading for success. Data migration is one of the key components in a successful implementation. The workshop includes general strategic considerations as well as specific topics like volumes, tooling, performance and validations.

## Slide 3: Data Management Strategy

## Slide 4: Data Management Strategy
Data preparation
What, Who, When, How
Roles and responsibilities
Defined for all elements of data migration
Approach
Who, what is the source, what data, acceptance criteria?
Defect triage, fix and re-execute
Define the defect identification, fixing and the iterative execution of data migration
Data management tools
Data management framework, LCS
Validation
Visual inspection, record count, comparison of reports between source & target, functional testing of critical scenarios etc.
Notes: Use this slide to talk a little bit about data migration in general and the different aspects listed – to get everyone on the same page and before starting the assessment.

## Slide 5: Planning and Strategy

## Slide 6: Data migration in the solution lifecycle
Testing with migrated data
Implement
Prepare
Initiate
Operate
Get ready to start
Design
Build
E2E/SIT
BAU/Cont. update
Go Live
UAT
Deploy
Cycle 1
UAT
Data validation test
Data Migration Strategy
Scope
Approach
Data management process
Tools
Functional requirements
Performance requirements
Cycle 2
Cycle 3
May not be a full cycle
Notes: Resources:​
Finance and Supply Chain Management: Data Management | February 14, 2020 - Microsoft Dynamics Blog​
  https://community.dynamics.com/365/b/techtalks/posts/dynamics-365-finance-scm-data-management-february-14-2020​
Data Migration | January 16, 2018 - Microsoft Dynamics Blog​
  https://community.dynamics.com/365/b/techtalks/posts/data-migration-january-16-2018

## Slide 7: Planning and Strategy
Describe the project timelines regarding data migration.
Add Info
(See slide notes for additional information)
Notes: Why are we asking this information?
We want to review how the data migration plan is incorporated into the overall project planning.
=========================
What to include?
Documents, diagrams, charts regarding the project’s timelines with a focus on data migration. Consider all phases of a project: Initiate, Implement, Prepare, Operate.
Examples would be project plan and data migration plan (including entities, dependencies, volumes, timings, iterations).
=========================

## Slide 8: Planning and Strategy
Data ownership
Add Info
(See slide notes for additional information)
Notes: Why are we asking this information?
We want to validate that the ownership of data is clearly defined and known to the team.
=========================
What to include?
Answers (in text or separate documents) to the following questions:
  Who owns the different steps of the data migration processes? Think here about steps like data extraction, provision and cleansing, importing it into the target environments.
  Which party assumes troubleshooting various issues? For example, if performance issues arise during data migration import, who can validate?
  Who is responsible of defining the data templates and formats?
  Who validates the data?
  Who signs off the data?
=========================

## Slide 9: Planning and Strategy
What type of data do you plan to migrate?
Add Info
(See slide notes for additional information)
Notes: Why are we asking this information?
We want to validate that the right type of data has been identified and that the data migration scope is clear.
The data mapping document will be an integral piece to the success of your data migration. This should include the transformation logic along with other checks like mandatory fields.
It’s important to complete data structures and relationship of the destination solution up front, otherwise data migration development will be delayed. Some projects might choose to define on an iterative basis throughout each sprints/iteration of your project and the project management team must be made aware that data migration development can be hindered until the destination solution entities and relationships are defined.
=========================
What to include?
Details, plans and documents regarding migrating the following types of data:
  Configuration data
  Master data vs Transaction data
  Historical data
  Processing large volumes of data or complexity of relationships amongst entities, time required to complete data migration can exceed planned cut over time. Hence, it is always advisable to have detailed data migration strategy which not only covers the right options to choose from for a project but also considers the volume and cut over time available.
=========================

## Slide 10: Planning and Strategy
Legacy systems and other sources of data; extraction and transformation of data.
Add Info
(See slide notes for additional information)
Notes: Why are we asking this information?
We want to validate that the right sources of legacy data have been identified.
Is there a proper plan to extract the data from these sources?
Have the necessary tools to extract and transport the data to the target systems been determined?
The data mapping document will be an integral piece to the success of your data migration. This should include the transformation logic along with other checks like mandatory fields.
It’s important to complete data structures and relationship of the destination solution up front, otherwise data migration development will be delayed. Some projects might choose to define on an iterative basis throughout each sprints/iteration of your project and the project management team must be made aware that data migration development can be hindered until the destination solution entities and relationships are defined.
=========================
What to include?
Information regarding all the legacy systems that will be a source of data, with their respective formats.
A description of the tools and processes to extract the data, clean it and to store it/ prepare it for import.
The owners of the above processes, if not presented already.
What is the plan for ensuring data cleansing prior to data migration? Migrating data incorrectly or incorrectly formatted can severely impact the quality of the migration as well performance.
The data load sequence is extremely important, and, in some cases, records will fail if not ordered in the correct sequence. All your references defined and loaded in the correct order?
=========================

## Slide 11: Planning and Strategy
Environment planning
Add Info
(See slide notes for additional information)
Notes: Why are we asking this information?
We want to validate that the environments involved in the data migration activities have been identified and a proper plan is defined for them.
=========================
What to include?
What environments do you plan to utilize for data migration activities? Include here source and target environments, staging and testing environments as well.
Environment planning that clearly defines when these environment will be made available and when will they become obsolete.
Assessments to define if the environments are sufficient, from a performance point of view.
=========================
Resources:​
Environment Planning for Finance and Operations Implementations | October 19, 2020 - Microsoft Dynamics Blog​
  https://community.dynamics.com/365/b/techtalks/posts/environment-planning-for-finance-and-operations-implementations-october-19-2020​
Environment planning - Finance & Operations | Dynamics 365 | Microsoft Docs​
  https://docs.microsoft.com/en-us/dynamics365/fin-ops-core/fin-ops/imp-lifecycle/environment-planning

## Slide 12: Planning and Strategy
Post Go-live strategy
Add Info
Add Info
Go-live strategy
Notes: Why are we asking this information?
We want to validate that the Go-live and post Go-live strategies have been considered and planned.
=========================
What to include?
Information about the Cutover plan and the Mock Go-live, including time frames.
How will the data be tested before Go-live?
Details about how you plan to handle data migration activities after Go-live. Include details about a subsequent Go-live, if applicable.
=========================
Resources:
Go-live Planning | August 9, 2018 - Microsoft Dynamics Blog
  https://community.dynamics.com/365/b/techtalks/posts/go-live-planning-8-9-18​

## Slide 13: Data Volume

## Slide 14: Data Volume
What data entities are planned for migration? How many records are currently planned to migrate?
See Solution Blueprint Template.xlsx
Please review and update the numbers.
SA: Please attach the latest SBR document to the invite
Notes: Why are we asking this information?
We want to validate that the volume of data being migrated has been assessed.
=========================
What to include?
The updated Solution Blueprint Template document (Excel file).
=========================

## Slide 15: Data Volume
How do you approach the migration of high volumes of data?
Add Info
(See slide notes for additional information)
Notes: Why are we asking this information?
We want to validate that the proper processes and tools to handle high volumes of data are in place.
=========================
What to include?
Any type of resources that focus on how high volumes of data will be managed. Think about all stages of data migration, including extraction, loading, synchronization.
How do you plan to use Dual write (if applicable) when looking at high volumes of data?
=========================

## Slide 16: Tooling

## Slide 17: Tooling
Tools for extracting data
Tools for transforming data
Tools for copying data between environments.
Add detailed info
Tools for copying / synchronizing data between applications
Add detailed info
Add detailed info
Add detailed info
Tools for loading data
Add detailed info
Tools for copying / synchronizing data between legal entities in the same environment
Add detailed info
Notes: Why are we asking this information?
We want to validate that the team has identified and validated the proper tools to be used in the data migration process.
=========================
What to include?
A description of the tools to be used at different stages of the data migration exercise.
High level logical steps and considerations for the implementation strategy of your selected migration tool.
=========================

## Slide 18: Performance

## Slide 19: Performance
Infrastructure considerations
Add Info
(See slide notes for additional information)
Notes: Why are we asking this information?
Performance is a key component of a successful data migration strategy – have the infrastructure aspects been analyzed and incorporated?
=========================
What to include?
A description of the actions taken to identify and agree on key infrastructure elements that influence data migration performance such as environment sizing or latency.
=========================

## Slide 20: Performance
Setup and tuning considerations
Add Info
(See slide notes for additional information)
Notes: Why are we asking this information?
Performance is a key component of a successful data migration strategy – how do you plan to tune the system for a better performance?
=========================
What to include?
A description of the actions taken to identify the available capabilities to improve performance and how these will be used. Examples include multithreading, synchronous vs asynchronous approaches, disabling database logging.
=========================
Resources:
Optimize data migration for Finance and Operations apps - Finance & Operations | Dynamics 365 | Microsoft Docs
  https://docs.microsoft.com/en-us/dynamics365/fin-ops-core/dev-itpro/sysadmin/optimize-data-migration
Recommendations for a performant data migration - Data migration in Power Platform and Dynamics 365 - Learn | Microsoft Docs

## Slide 21: Data Validation

## Slide 22: Data Validation
Describe the steps to ensure migrated data is valid and accurate (data quality, data formatting, etc.)
Add Info
(See slide notes for additional information)
Notes: Why are we asking this information?
We want to assert if data validation has been included in the overall planning.
=========================
What to include?
A description of the steps taken to validate the migrated data, for example to ensure that all the records have been added to the target system.
=========================

## Slide 23: Testing

## Slide 24: Testing
How do you plan to test the migrated data and document test results?
Add Info
(See slide notes for additional information)
Notes: Why are we asking this information?
We want to assert if testing plans exist for data migration cycles.
We want to validate that the testing results are injected into the next data migration cycle.
=========================
What to include?
Description, test cases, documentation that focuses on data migration testing.
If not covered already, information about ownership, for example, who signs off the data migration testing.
Description of the steps implemented to make sure the findings of a test cycle are brought to the next cycle.
=========================

## Slide 25: Q&A

## Slide 26: Q&A
Brief Q&A to discuss any additional topic areas.
List questions and follow up actions

## Slide 27: Thank you.